## Slide 1: Randomised Evaluation of COVID-19 Therapy: the RECOVERY trial
Site Set-up

## Slide 2: Steps to starting RECOVERY at your site
Regulatory
Nominate PI
Local R&D approval/contract
Training
Consent
Randomisation
Team
Roles
Capacity and redundancy
Receive “green light” e-mail
Follow-up
Background

## Slide 3: Regulatory
RECOVERY trial is high-priority public health trial and should take priority
RECOVERY is on CRN portfolio and your LCRN (or devolved nation equivalent) will support rapid trial set-up
All required documents and FAQs are available on the trial website (www.recoverytrial.net)
Pharmacy Assurance and FAQs section on website
No negotiation on contract (standard mNCA) and contract pre-signed by sponsor available on website
Send confirmation of Capacity and Capability, and fully executed contract (or e-mail from signatory) to recoverytrial@ndph.ox.ac.uk

## Slide 4: Training
This should begin while regulatory processes are ongoing
No delegation log required: Principal Investigator can decide who will do which procedures (based on experience and training)
No GCP training required
All staff must complete “Study background” training
Other training depends on role
  Consent training for those obtaining consent from participants
  Randomisation training for those using trial randomisation system
  Follow-up training for those completing 28 day Follow-up form
Staff must complete the Confirmation of Training form on website to indicate they have completed training

## Slide 5: Team
Principal Investigator takes overall responsibility for the trial at his/her site
Needs team of people who can take on various roles
  People to take consent (including research nurses). Can be done by clinical team caring for the patient
  People to randomise the participant. Not done at bedside but requires conversation with clinical team first to check history and any reasons why some arms of the trial may not be suitable
  People to complete Follow-up forms. Does not require patient contact but access to medical record
One person can do many roles, but up to PI to organise team efficiently

## Slide 6: Practicalities
Study treatment supply
  Please liaise with pharmacy to ensure hospital has treatments in stock
    Lopinavir-ritonavir available direct from DHSC (see website)
    Inhaled interferon-β only available from manufacturer
    Inform coordinating centre if some treatments unavailable
Identification of potential participants
  Please liaise with local testing lab so new cases are identified promptly and can be approached systematically. Every case should be given chance to participate unless a good reason otherwise
  Patient Information Sheet can be provided to participants while COVID-19 diagnostic test underway so they can consider

## Slide 7: Practicalities
Consent forms
  Guidance from NHS England Infection Control lead:
    The Consent Form remains with the individual obtaining the consent and not placed/left in the patients immediate environment
    The patient’s hands are decontaminated with soap and water or with alcohol hand wash
    The patient signs the consent form with a pen
    The signed paper consent form may leave the room without need for additional decontamination
    The pen stays with patient or is cleaned before leaving the room
    The person taking consent follows all other IPC guidance as instructed by Trust

## Slide 8: Questions
The trial website www.recoverytrial.net has a lot of information on it including Frequently Asked Questions so please look there
E-mail to recoverytrial@ndph.ox.ac.uk if no answer to your question on the website
Phone line for clinically urgent queries: 0800 1385451